## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project:
Week Of:
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
| 1 | Brian |  | duplication for words, finishing building dictionry files and jumbling words | Design and implementation of client gui and checking for winners
| 2 | Sunny |  | timer for 2 minutes, needs to be implemented in client-server and gui (backend and frontend) | Testing the timer
| 3 | Shreya |  | UML diagaram, code for shuffling words | implementation of client gui, testing intgrated components
| 4 | Ali |  | working on Client gui to integarte jumble words into gui, determine winner (set it up and test it) | Integration
Final Project Documentation | 5 | All